bide

GUEST TV PLATFORM

Scope of Works

& Developer Information Pack

Prepared for: Kyle Mendoza — Technology & Development, bide

Prepared by: David Liddell — bide Hotels

Template property: The View — 38 Shore Street, Thurso (9 rooms)

Scope: In-room guest TV platform — build, brand, integrate, replicate

Version 1.0 · August 2026 · Status: FOR BUILD

# Contents

# 1. Document purpose

This is the single reference document for the bide guest TV platform. It defines what is being built, what is in and out of scope, the phased plan, the technical requirements, the design, and the constraints. It is written to be uploaded to the developer environment and worked from directly. Where a decision is still open it is flagged [TO CONFIRM].

Read section 5 first. Phases 1a and 1b can be started immediately with no LG licence and no further sign-off. They are the fastest route to a branded, working guest experience.

# 2. Project overview

Turn the in-room TV from a plain television into a branded guest experience and a quiet ancillary-revenue channel. Built and proven once at The View, then cloned to every bide property. The screen greets the guest, tells the story of the building, guides the stay, and surfaces the right upsell at the right moment. Delivery is app-based over the existing Cat6 network — no coax, no aerial in rooms.

Guiding principles:

- Build once, clone everywhere. The View is the template; every setting travels by USB clone file.

- App-first, then branded. Guests get a good screen from day one; the branded Pro:Centric layer and personalisation follow.

- Bide Hotels only. The guest TV is a Hotels channel. No bide Investments content appears on it, ever.

- Unmanned-ready. Everything is remotely manageable and guest-proof, because there is no front desk.

# 3. Scope of works

## 3.1 In scope

- Configuration and lockdown of 9 x LG hospitality TVs at The View.

- A branded guest interface (welcome screen, navigation, content pages) in the bide identity.

- bide content pages (house guide, local guide, eat & drink, your stay) hosted and maintained by bide.

- LG Pro:Centric Cloud provisioning, interface build and remote management.

- MEWS integration for guest-name personalisation (later phase).

- An upsell and messaging engine keyed to stay stage (later phase).

- An owner welcome video slot.

- A cloning and replication method to roll the platform to every bide property.

## 3.2 Out of scope

- Live linear TV via an IPTV headend or aerial (explicitly excluded — app-based live channels only).

- Set-top boxes of any kind.

- Any third-party bespoke Pro:Centric app requiring the LG Developer Program (not our route).

- Physical cabling / first fix (contractor responsibility; assumed present and terminated).

- Any bide Investments content, integration or data.

# 4. Current state

Live now: all 9 TVs are installed and operating in standalone pass-through mode (Hotel Mode OFF). They behave as normal webOS 25 smart TVs. Guests have working apps and casting.

How we got here: the TVs shipped in hotel/Pro:Centric mode and hung on boot searching for a server that did not yet exist. Each was switched to pass-through via the installer menu (hold Settings until the menu clears, then 1-1-0-5-OK; alternate 9-8-7-6-OK).

Working today:

- iPlayer, ITVX, Channel 4, My5 (no login); Netflix / Prime via guest casting.

- QR casting (Google Cast + Apple AirPlay) with automatic guest-data wipe at checkout.

Implication: there is no guest-facing emergency. The branded build is an enhancement layered on a working service, and can be built calmly and cloned cleanly.

# 5. Immediate work (no licence required)

Priority. Two workstreams can start today. Neither depends on the LG licence, and neither is wasted — both slot straight into Pro:Centric later.

## 5.1 Phase 1a — server-less branded lockdown

Everything the TV does locally, configured once on a master set, then USB-cloned to all 9. No server, no licence, no cost beyond time.

- Master TV: set Country UK, connect network, sign into the no-login apps.

- Installer-menu lockdown: max volume cap, startup volume, boot straight to home screen, lock the settings menu, block unused ports, enable factory-reset protection.

- Branding: load a bide boot splash image via USB (the owner welcome video later occupies this same slot).

- Home launcher: pin and order the apps identically — iPlayer, ITVX, Channel 4, My5, then Netflix, Prime.

- Casting: confirm Google Cast + AirPlay QR pairing and checkout auto-wipe are enabled.

- Save the clone to USB (.tlx) and apply to the other 8. Retain the file — it seeds every future property.

Deliverable: all 9 rooms running an identical, locked, lightly-branded configuration, reproducible from one file.

## 5.2 Phase 1b — bide content pages (HTML5)

Build the guest content as lightweight, TV-first HTML5 pages hosted on a bide domain, so they update without touching a single TV. These are the same pages Pro:Centric will surface later, so building them now is a head start, not throwaway work.

| Page | Content |
| --- | --- |
| Welcome / home | Greeting, room, checkout, WiFi, six-tile navigation |
| House guide | Heating, hot water, quirks of a heritage building, how to reach the team |
| Explore the NC500 | bide's own local picks — Dunnet Head, beaches, distilleries, Orkney ferry |
| Eat & drink | Honest local recommendations |
| Your stay | Late checkout, bill, message the team, book direct / bide Club |

Build spec: responsive, TV-first (1920 x 1080), remote-navigable, matched to the approved design (section 10). Host on the existing bide stack / Railway. Content editable by the ops team without a developer where possible.

# 6. Hardware specification

Group standard: LG 43UK762H — UK/EU spec, full code 43UK762H0LB.AEK. Current model on webOS 25; directly replaces the older UR762H and UM662H. Every room that can take a 43" uses this exact model so a single clone works across the estate.

| Attribute | Specification |
| --- | --- |
| Model / code | LG 43UK762H — 43UK762H0LB.AEK (UK/EU) |
| Platform | webOS 25 · Pro:Centric Smart (Direct / Cloud ready) |
| Panel | 43" 4K UHD NanoCell · HDR10 Pro / HLG · 265 cd/m² |
| Dimensions | 967 x 564 x 57.1 mm (no stand) · 8.8 kg |
| Mounting | VESA 200 x 200 mm · no stand supplied (wall-mount only) |
| Tuner | Freeview DVB-T2/C/S2 built-in (unused — no aerial in rooms) |
| Connectivity | HDMI x3 · USB x2 · RJ45 · Wi-Fi · SoftAP · CI slot · RS-232C |
| Casting | Google Cast + Apple AirPlay · QR pairing · checkout wipe |
| Hospitality | Pro:Centric, EzManager, USB cloning, hotel mode, welcome video/screen, Wake-on-LAN, SNMP, IP diagnostics |
| Warranty | 3-year manufacturer on-site swap-out |

## 6.1 Mounting standard

Slim micro-gap flush mount (sits ~9 mm off the wall) on VESA 200 x 200, with a recessed power + Cat6 outlet behind each TV so the screen sits flush with no visible cabling. This is the bide install standard for every property.

## 6.2 32" exception

There is no 32" in the UK762H family. If a room physically cannot take a 43", the fallback is the LG 32LN661H — but it is HD and webOS 22, a different platform that needs its own separate configuration and clone. Avoid unless forced; treat any unit as a deliberate, separately-managed exception.

## 6.3 Redundant units

The displaced Bush 43FT24CA sets are to be redeployed (staff areas, Elderberry Hall interim, or resale), not scrapped.

# 7. System architecture

Three layers, from the TV outward:

| Layer | What it is | Owner | Needs licence? |
| --- | --- | --- | --- |
| 1 — TV local | Hotel mode, lockdown, splash, app launcher, casting | bide / Kyle | No |
| 2 — Pro:Centric | Branded portal, remote management, guest personalisation | LG platform | Yes |
| 3 — bide content & data | HTML5 pages, MEWS middleware, upsell routing | bide / Kyle | No |

Data flow (target state): MEWS → middleware → Pro:Centric portal renders guest name / room / checkout → TV. Upsell actions flow back to MEWS (operational) or GHL (marketing). If MEWS is unreachable, the screen falls back to a non-personalised welcome — never blank or broken.

# 8. Build phases

| Phase | Deliverable | Licence? | Status |
| --- | --- | --- | --- |
| 0 | Pass-through launch | No | Done — live |
| 1a | Server-less branded lockdown + clone | No | Start now |
| 1b | bide HTML5 content pages | No | Start now |
| 1c | Pro:Centric Cloud branded interface | Yes | On purchase |
| 2 | MEWS guest-name personalisation | Yes | Later |
| 3 | Upsell & messaging engine | Partly | Later |
| 4 | Owner welcome video | No | Film soon |
| 5 | Portfolio replication | No | After The View |

Phase 1c — Pro:Centric Cloud interface

Build the branded portal in the Cloud Admin Client using LG's Project Editor, matching the approved design. Map the home screen, surface the bide content pages, and enable one-click remote management of all 9 TVs. Point each TV at the Cloud server (section 9), configure one master, clone out.

Phase 2 — MEWS personalisation

Middleware pulls guest first name, room name, checkout date/time and booking channel from the MEWS API; the welcome screen renders these on check-in and resets at checkout. Name and stay dates only on the TV layer — no payment or contact data, nothing persisted post-checkout.

Phase 3 — Upsell & messaging engine

Offers keyed to stay stage, routed to MEWS (operational) or GHL (marketing). See the matrix below. Editable by the ops team.

| Moment | Offer | Route |
| --- | --- | --- |
| Arrival | Welcome video, no selling | TV only |
| Mid-stay | Experiences (NC500, whisky, golf — commission), eat & drink | Partner / GHL |
| By 8pm | Breakfast hamper / produce box for AM delivery | MEWS + ops task |
| Gap night | “Stay another night, one tap” when tomorrow is unsold | MEWS availability |
| Final evening | Late checkout + book-direct + bide Club | MEWS / GHL |
| Aurora / weather | KP-index alert; indoor picks in poor weather | Weather API, editable |

Phase 4 — Owner welcome video

60–90 seconds, David and Sam to camera at the property, captioned. Plays on first power-on after check-in; replayable from the House Guide tile. Occupies the same slot as the Phase 1a splash. Per-property versions use the same skeleton.

Phase 5 — Replication

Master config and clone file per property, The View as template. Per-property variants recolour the horizon motif and swap the local content and video; the system is not rebuilt. Order of roll-out to follow The View sign-off.

# 9. Pro:Centric Cloud — procurement & provisioning

Route (confirmed with JP-UK): Pro:Centric Cloud is a per-display, per-year subscription. LG UK does not permit self-serve subscribe, but JP-UK sells it directly — product PCC-30CL (Pro:Centric Cloud, 1-year), one per TV. JP-UK have confirmed both our models (43UK762H and 32LN661H) are supported.

Steps:

- Purchase 9 x PCC-30CL from JP-UK (one per TV at The View).

- Assign the subscription to the bide LG Business Cloud workspace (Business Administrator: david@liddellpropertyinvestments.com).

- Add Kyle as a user/role on the workspace.

- Build the branded portal in the Cloud Admin Client.

- On each TV, set installer-menu item 098 (Pro:Centric) and 119 (Data Channel) to the Cloud server. Configure the master, distribute by .tlx clone.

TO CONFIRM before purchase: (1) per-display price and any break on 9; (2) which tier PCC-30CL is (Standard vs Premium) and that it includes the branded portal editor and MEWS guest-name personalisation; (3) that the subscription assigns to the david@ workspace.

Not our route: a third-party bespoke Pro:Centric app would require its developer to join the LG Pro:Centric Developer Program. We are not doing this — Kyle builds inside the Admin Client with LG's own tools.

# 10. Design specification

The approved working mockup bide_tv_welcome_screen.html is the visual contract. Build the Pro:Centric portal and the HTML content pages to match it.

- Deep Fir Green ground; a single thin Gorse Yellow horizon line as the signature motif (the last light over the Pentland Firth).

- “Fàilte, [name]” greeting, guest name in gorse (MEWS-fed in Phase 2; static until then).

- Six-tile navigation rail: Watch · Cast your phone · House guide · Explore the NC500 · Eat & drink · Your stay.

- Always-on WiFi name/password; a “wiped at checkout” trust line.

- Quiet, minimal, honest tone throughout.

Typography: production uses licensed TT Ramillas (display, licence held by Asa / WorkByPage) and Jost (UI/body). The mockup's Fraunces is a stand-in only.

# 11. Brand & compliance constraints

Channel firewall (hard rule): the guest TV is bide Hotels only. No bide Investments content, links, data or messaging on any screen, tile, page or video — ever.

## 11.1 Palette

| Token | Hex |
| --- | --- |
| Fir Green | #172D23 |
| Gorse Yellow | #FAB30C |
| Slate Black | #191D1B |
| Stone Grey | #F9F8F3 |

## 11.2 Compliance

- TV Licensing: hotel/mobile-units rate held per property before go-live (covers the first 15 rooms).

- Streaming: guests use their own accounts via QR casting; no shared house logins preloaded. Checkout auto-wipe is the compliance backbone — test it on every rollout.

- Guest data: name + stay dates only on the TV layer; nothing persists on the set post-checkout. Add to the bide Comply privacy register.

# 12. Access, credentials & dependencies

| Item | Source / owner | When |
| --- | --- | --- |
| LG Business Cloud workspace access | David adds Kyle as user/role | On licence purchase |
| Design mockup (bide_tv_welcome_screen.html) | Provided | Ready |
| Brand assets + TT Ramillas licence | Asa / WorkByPage | Request now |
| bide domain + hosting | David / existing stack | Ready |
| MEWS API credentials | David | Phase 2 |
| GHL sub-account (Hotels) | David | Phase 3 |
| Weather / KP-index API | Kyle to propose | Phase 3 |

# 13. Deliverables & acceptance

| # | Deliverable | Accepted when |
| --- | --- | --- |
| 1 | Server-less lockdown + clone (1a) | All 9 identical from one clone; guest-proof; casting wipes |
| 2 | bide content pages (1b) | All pages live, on-brand, editable, TV-navigable |
| 3 | Pro:Centric branded interface (1c) | Matches mockup; Asa signs off brand fidelity; remote mgmt works |
| 4 | MEWS personalisation (2) | Name/room/checkout render on check-in; clean fallback proven |
| 5 | Upsell engine (3) | All matrix moments firing; requests land in MEWS/GHL |
| 6 | Welcome video (4) | Plays on first power-on; captioned; replayable |
| 7 | Replication method (5) | Second property stood up from template in under a day on site |

# 14. Open items & decisions

- Pro:Centric subscription — buy 9 x PCC-30CL from JP-UK; confirm price, tier and personalisation coverage; assign to workspace.

- Late checkout fee + gap-night discount — David to set before the upsell engine.

- Hamper / produce partner — Samantha.

- Owner welcome video — David + Sam to film.

- Final brand assets — Asa (TT Ramillas, wordmark files).

- Broadband headroom check — confirm 9 rooms streaming HD concurrently (≈ 45–70 Mbps) before scale.

# Appendix A — Quick reference

| Key | Value |
| --- | --- |
| TV model | LG 43UK762H — 43UK762H0LB.AEK (webOS 25) |
| VESA | 200 x 200 mm |
| Installer menu | Hold Settings → 1-1-0-5-OK (alt 9-8-7-6-OK) |
| Pass-through | Installer menu → Hotel Mode OFF |
| Pro:Centric TV items | 098 (Pro:Centric) · 119 (Data Channel) |
| Clone file | USB .tlx (master → all sets) |
| Pro:Centric licence | JP-UK PCC-30CL — Cloud, per-display 1-yr (x9) |
| LG portal | lgbusinesscloud.com — admin: david@liddellpropertyinvestments.com |
| TV supplier | JP-UK — jp-uk.co.uk · 0161 474 1200 · Jacob@jp-uk.co.uk |
| Brand assets | Asa Rodger / WorkByPage |
| Property | The View, 38 Shore Street, Thurso — 9 rooms |

# Appendix B — Glossary

| Term | Meaning |
| --- | --- |
| Pass-through mode | Hotel mode off; TV runs as a standard smart TV |
| Pro:Centric | LG's hospitality TV management platform (Cloud or Direct) |
| Pro:Centric Cloud | LG-hosted version; browser Admin Client; per-TV annual subscription |
| .tlx clone file | USB file carrying a master TV's full configuration to other sets |
| Installer menu | Hidden TV setup menu for hotel-mode and Pro:Centric settings |
| EzManager | On-TV setup wizard for hospitality configuration |
| SoftAP | TV acts as a Wi-Fi access point for guest device pairing |
| MEWS | bide's property management system (bookings, guests, availability) |
| GHL | Go High Level — bide's CRM (separate Hotels / Investments sub-accounts) |